## Plan
task | description | executor | duration | predecessors
Requirements | Agree scope and acceptance criteria. | Anna | 2
Solution design | Prepare the implementation design. | Elena | 3 | Requirements
Implementation | Build and review the solution. | Mikhail | 5 | Solution design
Release | Complete final verification and release. | Daria | 1 | Implementation