## Plan
task | description | executor | duration | predecessors
Phase 01 - Scope definition | Import test activity 1 for Small import test. | Anna | 1
Phase 01 - Protocol design | Import test activity 2 for Small import test. | Elena | 2 | Phase 01 - Scope definition
Phase 01 - Material preparation | Import test activity 3 for Small import test. | Mikhail | 3 | Phase 01 - Scope definition
Phase 01 - Method development | Import test activity 4 for Small import test. | Daria | 4 | Phase 01 - Protocol design, Phase 01 - Material preparation
Phase 01 - Experiment execution | Import test activity 5 for Small import test. | Pavel | 5 | Phase 01 - Method development
Phase 02 - Quality review | Import test activity 6 for Small import test. | Anna | 6 | Phase 01 - Experiment execution
Phase 02 - Data analysis | Import test activity 7 for Small import test. | Elena | 7 | Phase 02 - Quality review
Phase 02 - Evidence review | Import test activity 8 for Small import test. | Mikhail | 1 | Phase 02 - Quality review
Phase 02 - Documentation | Import test activity 9 for Small import test. | Daria | 2 | Phase 02 - Data analysis, Phase 02 - Evidence review
Phase 02 - Readiness review | Import test activity 10 for Small import test. | Pavel | 3 | Phase 02 - Documentation