## Plan
task | description | executor | duration | predecessors
Phase 01 - Scope definition | Import test activity 1 for Medium import test. | Anna | 1
Phase 01 - Protocol design | Import test activity 2 for Medium import test. | Elena | 2 | Phase 01 - Scope definition
Phase 01 - Material preparation | Import test activity 3 for Medium import test. | Mikhail | 3 | Phase 01 - Scope definition
Phase 01 - Method development | Import test activity 4 for Medium import test. | Daria | 4 | Phase 01 - Protocol design, Phase 01 - Material preparation
Phase 01 - Experiment execution | Import test activity 5 for Medium import test. | Pavel | 5 | Phase 01 - Method development
Phase 02 - Quality review | Import test activity 6 for Medium import test. | Anna | 6 | Phase 01 - Experiment execution
Phase 02 - Data analysis | Import test activity 7 for Medium import test. | Elena | 7 | Phase 02 - Quality review
Phase 02 - Evidence review | Import test activity 8 for Medium import test. | Mikhail | 1 | Phase 02 - Quality review
Phase 02 - Documentation | Import test activity 9 for Medium import test. | Daria | 2 | Phase 02 - Data analysis, Phase 02 - Evidence review
Phase 02 - Readiness review | Import test activity 10 for Medium import test. | Pavel | 3 | Phase 02 - Documentation
Phase 03 - Scope definition | Import test activity 11 for Medium import test. | Anna | 4 | Phase 02 - Readiness review
Phase 03 - Protocol design | Import test activity 12 for Medium import test. | Elena | 5 | Phase 03 - Scope definition
Phase 03 - Material preparation | Import test activity 13 for Medium import test. | Mikhail | 6 | Phase 03 - Scope definition
Phase 03 - Method development | Import test activity 14 for Medium import test. | Daria | 7 | Phase 03 - Protocol design, Phase 03 - Material preparation
Phase 03 - Experiment execution | Import test activity 15 for Medium import test. | Pavel | 1 | Phase 03 - Method development
Phase 04 - Quality review | Import test activity 16 for Medium import test. | Anna | 2 | Phase 03 - Experiment execution
Phase 04 - Data analysis | Import test activity 17 for Medium import test. | Elena | 3 | Phase 04 - Quality review
Phase 04 - Evidence review | Import test activity 18 for Medium import test. | Mikhail | 4 | Phase 04 - Quality review
Phase 04 - Documentation | Import test activity 19 for Medium import test. | Daria | 5 | Phase 04 - Data analysis, Phase 04 - Evidence review
Phase 04 - Readiness review | Import test activity 20 for Medium import test. | Pavel | 6 | Phase 04 - Documentation
Phase 05 - Scope definition | Import test activity 21 for Medium import test. | Anna | 7 | Phase 04 - Readiness review
Phase 05 - Protocol design | Import test activity 22 for Medium import test. | Elena | 1 | Phase 05 - Scope definition
Phase 05 - Material preparation | Import test activity 23 for Medium import test. | Mikhail | 2 | Phase 05 - Scope definition
Phase 05 - Method development | Import test activity 24 for Medium import test. | Daria | 3 | Phase 05 - Protocol design, Phase 05 - Material preparation
Phase 05 - Experiment execution | Import test activity 25 for Medium import test. | Pavel | 4 | Phase 05 - Method development