## Plan
task | description | executor | duration | predecessors
Target discovery | Define target profile and evidence package | Elena | 4
Assay development | Build and qualify the primary screening assay | Mikhail | 6 | Target discovery
Compound library prep | Curate and plate the focused compound library | Daria | 5 | Target discovery
Primary screening | Run screen and complete quality control | Mikhail | 8 | Assay development, Compound library prep
Hit analysis | Normalize results and select confirmed hits | Anna | 4 | Primary screening
Hit confirmation | Dose response and orthogonal confirmation | Elena | 7 | Hit analysis
Early ADME | In vitro stability and permeability panel | Daria | 6 | Hit analysis
Safety panel | Early off-target and cytotoxicity panel | Pavel | 5 | Hit analysis
Lead selection | Review evidence and nominate lead series | Anna | 3 | Hit confirmation, Early ADME, Safety panel
Process development | Develop initial synthesis and control strategy | Elena | 7 | Lead selection
Regulatory package | Prepare pre-IND briefing materials | Pavel | 6 | Lead selection
Candidate review | Cross-functional candidate readiness review | Anna | 2 | Process development, Regulatory package